## 工作表1
RIsk | Description | Severity | Likelihood | Risk Impact | Control
Technical
Limits on AI Search API Calls | Due to call constraints, third-party AI search services may not be able to manage a high volume of concurrent requests or provide fast search results. | Generally unacceptable | Possible | High | Strategies include clever request queuing and caching to minimise repeat requests and using numerous API service providers as backups.
Crawler failure on site structure change | The HTML format of websites like government statistics bureaux and libraries might change at any moment, which makes it hard for crawlers to get data correctly. | Generally unacceptable | Likely | High | Keep an eye on data sources on a regular basis, use adaptive crawling logic, and set up a quick update system.
Performance issues in concurrent/batch searches | High concurrency or handling a lot of batch queries might result in timeouts or sluggish response times. | Generally unacceptable | Possible | High | Optimise database queries, implement scalable architecture and conduct stress testing.
Metadata extraction accuracy below target | Metadata extraction might not achieve the 95% accuracy threshold. | Generally unacceptable | Possible | High | Enhance parsing algorithms, employ human review for important data, and add further validation levels.
Operational
NDA violations or security lapses | Inadequate access control or encryption may lead to confidentiality agreements being broken or data leaks occurring. | Generally unacceptable | Unlikely | High | Maintain complete audit logs, implement stringent access control, encrypt data both in transit and at rest, and carry out frequent security audits.
Budget overruns from API usage or storage costs | Large-scale storage or excessive API requests may cost more than the budgeted amount. | Tolerable | Possible | Medium | Monitor usage, set cost alerts, and optimize API calls and storage retention policies.
Team member unavaliability | Team member might be unvailable due too illness, injury or other personal reasons, which could delay project progress. | Tolerable | Possible | Medium | Distribute tasks to avoid singnle points of failure, kepp regular progress updates, and ensure all the members have an acess to necessary project resources.
External
Loss of access to key data sources | Due to technical limitations, permissions, or policy, some essential data sources might no longer be accessible. | Generally unacceptable | Unlikely | High | Maintain backup sources and make contracts with suppliers.
Legal and compliance issues with data scraping | Certain scraping operations can be against the terms of service of the target website or the law. | Generally unacceptable | Possible | High | Examine the terms of service, abide by the guidelines in robots.txt, and, if required, seek legal authority.